## Estimation
2620 Nokia Care Academy L&A portal Functional Overview Status | [12 empty] | Man Days
ID | Spec. Sec. | Functionality | Page | Status | Development Phase | From TT | From UI | From AD | Dev Name | From QC | Queries | Responses | GR | UI | AD | QC | Total
1 | 5 | Nokia Care Portal Overview | 8 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
2 | 5.1 | Language Settings | 8 | Scheduled | Phase 2B | N/A | 2014-01-10 | 2014-01-11 | DS | 2014-02-10 |  |  | 0 | 0.5 | 0.5 | 0.2 | 1.2
3 | 5.2 | Accessing the Portal | 8 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
4 | 5.2.1 | Self Registration | 8 | Partially Done | TBC | [5 empty] | Do we need to work on self registration module? | [MWP 09.01] No | TBC | TBC | TBC | TBC | 0
5 | 5.2.2 | Subsequent Access | 9 | Finished | Phase 1 | [11 empty] | 0
6 | 5.3 | Administrative Rights | 9 | Finished | Phase 1 | [11 empty] | 0
7 | 6 | Learner Section | 9 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
8 | 6.1 | Global Elements | 11 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
9 | 6.1.1 | Navigation (HLS – 5) ['View people' panel - available as the 2nd item from the profile dropdown menu. Opens a panel listing alphabetically all people sharing a community with the learner. Each entry has summary details as per the Profile bubble, plus button to follow (or indicator that they are follow/follower already) - refer to other/final Profile bubble mock-ups] | 11 | Partially Done | Phase 2B | N/A | 2014-01-16 | 2014-01-22 |  | 2014-02-10 |  |  | 1 | 5 | 3 | 1.8 | 10.8
10 | 6.1.2 | Search (HLS – 6) [Display search box with filters to limit search and different search result will be shown in individual tabs] | 11 | Scheduled | Phase 3 | [7 empty] | 2 | 10 | 10 | 4.4 | 26.4
11 | 6.1.3 | Accreditation alert (HLS – 7) | 12 | In Progress | Phase 2A | [11 empty] | 0
12 | 6.1.4 | Notifications panel (HLS – 8) [Define notification types, mockup for each type of notification item, separate notification panel design and settings to control notification from profile settings] | 12 | Scheduled | Phase 3 | [7 empty] | 1 | 4 | 4 | 1.8 | 10.8
13 | N/A | Profile bubble [clickable links, follow/unfollow and allow mouse hover on profile bubble] | N/A | Partially Done | Phase 2B | N/A | 2014-01-07 | 2014-01-15 |  | 2014-02-10 |  |  | 0 | 2 | 2 | 0.8 | 4.8
14 | 6.2 | Home View | 13 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
15 | 6.2.1 | Accreditation level badge (HLS – 9) | 13 | In Progress | Phase 2A | [11 empty] | 0
16 | 6.2.2 | Profile summary (HLS – 10) | 14 | Finished | Phase 1 | [5 empty] | No work pending in profile summary |  | N/A | N/A | N/A | N/A | 0
17 | 6.2.3 | Action form (HLS – 11) [Share an update, praise someone] | 14 | Partially Done | Phase 2B | N/A | 2014-01-18 | 2014-01-25 | DS | 2014-02-10 |  |  | 0 | 4 | 3 | 1.4 | 8.4
18 | 6.2.4 | Recent activity log (HLS – 12) | 14 | Partially Done | Phase 2B | N/A | N/A | 2014-01-17 |  | 2014-02-10 |  |  | 0 | 0 | 2 | 0.4 | 2.4
19 | 6.2.5 | Communities circle (HLS – 13) [Completed community] | 14 | Partially Done | Phase 3 | 2014-01-17 | N/A | N/A |  | N/A | Can we move this also as it won't add much but takes a lot of time? |  | 0 | 7 | 1 | 1.6 | 9.6
20 | 6.2.6 | Community view | 15 | Finished | Phase 1 | [11 empty] | 0
21 | 6.2.7 | Learning activity status (HLS – 14) | 15 | Finished | Phase 1 | [11 empty] | 0
22 | 6.2.8 | Action form (HLS – 15) [This will be implemented after 6.2.3] | 15 | Partially Done | Phase 2B | N/A | 2014-01-18 | 2014-01-27 | DS | 2014-02-10 |  |  | 0 | 2 | 2 | 0.8 | 4.8
23 | 6.2.9 | Community activity summary (HLS – 16) | 16 | Scheduled | Phase 2B | 2014-01-20 | 2014-01-21 | 2014-01-27 | DS/KBS | 2014-02-10 | How the community contribution is calculated? We need confirmation from client. | [MWP 09.01] I need to work on this. What we have in previous mock-ups for community activity is not strictly accurate, but it will be based on how much social activity (i.e. any posts, likes, rates, follows etc) that the learner undertakes. [VM 10.01] Can you confirm when can we expect these details as it might impact delivery? | 0 | 2 | 1 | 0.6 | 3.6
24 | 6.2.10 | Learning circle (HLS – 17) | 16 | Finished | Phase 1 | [11 empty] | 0
25 | 6.2.11 | Follows circle (HLS – 18) [1) A circular list of ‘people discs’ giving access to all the users the user is following or followers of the user within the community 2) Selecting a people disc will display that users Personal Profile panel 3) Ability to switch between their own follows and all learners in the community] | 16 | Scheduled | Phase 2B | 2014-01-10 | 2014-01-20 | 2014-01-30 |  | 2014-02-10 | What all information we can display in profile panel after clicking on follow circle? | [MWP 09.01] For functionality point 2, viewing someone elses Personal Profile should display all user info - however both Admin and the Learner should have control over what info is displayed to others - As we've discussed before. [VM 10.01] Do you mean same personal profile currently shown to user with all tabs and information? Can we discuss? For functionality point 3, I think we can double up here with ID9 the 'View People' panel, selecting the followers ring itself will open the 'View People' panel and display all learners within that community. So the 'View People' panel needs to have filter functionality (available to the learner) so they can filter by each community or all communities they are assigned to. - We can discuss further. [VM 10.01] But in point 2 you said to open personal profile, in here you want view people. Can we discuss? | 1 | 3 | 3 | 1.4 | 8.4
26 | 6.2.12 | Communities circle (HLS – 19) | 16 | Finished | Phase 1 | [11 empty] | 0
27 | 6.3 | Community – Activity Launch view | 17 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
28 | 6.3.1 | Current Activity information (HLS – 20) | 17 | Finished | Phase 1 | [11 empty] | 0
29 | 6.3.2 | Action form (HLS – 21) | 17 | Finished | Phase 1 | [11 empty] | 0
30 | 6.3.3 | Activity action log (HLS – 22) [Activity Likes - #10493 and display of like popup] | 18 | Partially Done | Phase 2B | N/A | N/A | 2014-01-31 | DS | 2014-02-10 |  |  | 0 | 0 | 0.5 | 0.1 | 0.6
31 | 6.3.4 | Learning circle (HLS – 23) | 18 | Finished | Phase 1 | [11 empty] | 0
32 | 6.3.5 | Follows circle (HLS – 24) [Will be implemented with home view] | 18 | Scheduled | Phase 2B | N/A | 2014-01-21 | 2014-01-31 |  | 2014-02-10 |  |  | 0 | 1 | 1 | 0.4 | 2.4
33 | 6.3.6 | Communities circle (HLS – 25) | 18 | Finished | Phase 1 | [11 empty] | 0
34 | 6.4 | Community – Activity panel | 19 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
35 | 6.4.1 | Current Activity information (HLS – 27) | 19 | Finished | Phase 1 | [11 empty] | 0
36 | 6.4.1 | Preview Documents | 19 | Scheduled | Phase 3 | [7 empty] | TBC | TBC | TBC | TBC | 0
37 | 6.4.2 | Action form (HLS – 28) | 19 | Finished | Phase 1 | [11 empty] | 0
38 | 6.4.3 | Tracking (HLS – 28) | 19 | In Progress | Phase 2A | [11 empty] | 0
39 | 6.5 | Personal profile panel | 20 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
40 | 6.5.1 | Personal details (HLS – 31) | 20 | Finished | Phase 1 | [11 empty] | 0
41 | 6.5.2 | Description (HLS – 32) | 20 | Finished | Phase 1 | [11 empty] | 0
42 | 6.5.3 | Skills and expertise areas (HLS – 33) [Ability to add skills and expertise with total experience] | 20 | Scheduled | Phase 3 | [7 empty] | 0.5 | 2 | 1.5 | 0.8 | 4.8
43 | 6.5.4 | Interests and qualifications (HLS – 34) [Ability to add interests and qualification later shown in personal profile panel] | 20 | Scheduled | Phase 3 | [7 empty] | 0.5 | 2 | 1.5 | 0.8 | 4.8
44 | 6.5.5 | Personal Account preferences/settings (HLS – 35) [Ability to turn on/off notifications, selection of language preferences and settings] | 20 | Partially Done | Phase 3 | [5 empty] | What will be the Accessibility – display style/settings choice? | [MWP 09.01] For Ease of Access (accessibility settings) we'd follow the model used by e-learning CDF settings - but likely we'll remove this from Phase 2B [VM 10.01] We are doing notification and language only in this phase. | 0.5 | 2 | 2 | 0.9 | 5.4
45 | 6.5.5 | Personal Account preferences/settings (HLS – 35) | 20 | Partially Done | Not applicable | [11 empty] | 0
46 | 6.5.7 | Learning activity history (HLS – 37) | 21 | Partially Done | Phase 3 | 2014-01-10 | TBC | TBC |  | TBC | Could you please explain reviews? | [MWP 09.01] Reviews are where a learner writes a review of the activity - so effectively what they wrote when recommending [VM 10.01] Where will it be displayed in activity history? | TBC | TBC | TBC | TBC | 0
47 | 6.5.8 | Accreditation Status | 21 | Finished | Phase 1 | [11 empty] | 0
48 | 6.5.9 | Learning bookmarks (HLS – 38) | 21 | Scheduled | Phase 3 | [5 empty] | How the learning bookmark will work? | [MWP 09.01] In the Personal Profile panel the bookmark list will be a list of activities the learner has bookmarked, they should also have the ability to remove (after confirmation) an activity from their bookmark list We are missing the mechanism to bookmark activities. Suggest a toggable icon (which also acts as an indicator to show when an activity has been bookmarked) selecting will either add or remove from the bookmark list. Suggest this appears on the Launch view and activity panel. | 2 | 2 | 3 | 1.4 | 8.4
49 | 6.5.10 | Community activity history (HLS – 39) [All community specific activities and sorting] | 21 | Scheduled | Phase 2B | N/A | 2014-01-23 | 2014-02-03 |  | 2014-02-10 | We are assuming it will be activity history of all users for communities user is member of? | [MWP 09.01] As per the HLS, just their follows and following [VM 10.01] Alright | 0 | 1 | 2 | 0.6 | 3.6
50 | 6.5.11 | Followers (HLS – 40) | 21 | Scheduled | Phase 2B | N/A | 2014-01-24 | 2014-01-25 | DS | 2014-02-10 |  |  | 0 | 0.5 | 0.5 | 0.2 | 1.2
51 | 6.5.12 | Following (HLS – 41) | 21 | Scheduled | Phase 2B | N/A | 2014-01-24 | 2014-01-26 | DS | 2014-02-10 |  |  | 0 | 0.5 | 0.5 | 0.2 | 1.2
52 | 6.5.13 | Profile completion (HLS – 42) | 21 | Scheduled | Phase 3 | [5 empty] | We need to define certain rules to calculate profile completion. Please suggest. | [MWP 09.01] We would take all the parts of the profile a learner can update for themselves and then average a percentage based on how many are completed. However this would also prompt the learner to complete each part (in order) as well. Suggest we remove this from Phase 2B. | TBC | TBC | TBC | TBC | 0
53 | 7 | Administration Section (HLS – 43) [Mantis #10446] | 22 | See below | Phase 2B | N/A | N/A | 2014-01-10 |  | 2014-01-25 |  |  | 0 | 0 | 1 | 0 | 1
54 | n/a | Admin Home | n/a | Finished | Phase 1 | [11 empty] | 0
55 | 7.1 | User Management | 22 | Finished | Phase 1 | [11 empty] | 0
56 | n/a | User Listing + Actions | n/a | Finished | Phase 1 | [11 empty] | 0
57 | 7.1.1 | Manual User Creation (HLS – 45) | 22 | Finished | Phase 1 | [11 empty] | 0
58 | 7.1.2 | Import Users (Create Multiple Users) (HLS – 45) | 24 | Finished | Phase 1 | [11 empty] | 0
59 | 7.1.3 | Export Users (HLS – 45) | 26 | Finished | Phase 1 | [11 empty] | 0
60 | 7.1.5 | Manage Roles | 27 | Finished | Phase 1 | [11 empty] | 0
61 | 7.2 | Community Management | 27 | Finished | Phase 1 | [11 empty] | 0
62 | n/a | Community Listing + Actions | n/a | Finished | Phase 1 | [11 empty] | 0
63 | 7.2.1 | Create Community (HLS – 47) | 27 | Finished | Phase 1 | [11 empty] | 0
64 | 7.2.2.1 | User Assignment | 29 | Finished | Phase 1 | [11 empty] | 0
65 | 7.2.2 | Edit Community (HLS – 47) | 28 | Finished | Phase 1 | [11 empty] | 0
66 | 7.2.2.2 | Community Assignment | 29 | Finished | Phase 1 | [11 empty] | 0
67 | 7.2.3 | Edit Community display order | 29 | Finished | Phase 1 | [11 empty] | 0
68 | 7.3 | Activity Management | 29 | Finished | Phase 1 | [11 empty] | 0
69 | n/a | Activity Listing + Actions | n/a | Finished | Phase 1 | [11 empty] | 0
70 | 7.3.1 | Create a Activity (HLS – 47) | 29 | Finished | Phase 1 | [11 empty] | 0
71 | 7.3.2 | Activity listing and Filters | 30 | Finished | Phase 1 | [11 empty] | 0
72 | 7.3.3 | Edit Activity: (HLS – 47) | 31 | Finished | Phase 1 | [11 empty] | 0
73 | 7.3.3.1 | Activity Assignment | 32 | Finished | Phase 1 | [11 empty] | 0
74 | 7.3.3.1 | Community Assignment | 32 | Finished | Phase 1 | [11 empty] | 0
75 | 7.3.4 | Assess Activities | 32 | In Progress | Phase 2A | [11 empty] | 0
76 | 7.4 | Accreditation Management | 34 | Finished | Phase 1 | [11 empty] | 0
77 | n/a | Accreditation Listing + Actions | n/a | Finished | Phase 1 | [11 empty] | 0
78 | 7.4.1 | Create Accreditation (HLS – 46) | 34 | Finished | Phase 1 | [11 empty] | 0
79 | 7.4.2 | Edit Accreditation (HLS – 46) | 34 | Finished | Phase 1 | [11 empty] | 0
80 | n/a | Accreditation Set Listing + Actions | n/a | Finished | Phase 1 | [11 empty] | 0
81 | 7.4.3 | Create Accreditation Set | 35 | Finished | Phase 1 | [11 empty] | 0
82 | 7.4.4 | Edit Accreditation Set | 36 | Finished | Phase 1 | [11 empty] | 0
83 | 7.4.4.1 | Element assignment to accreditation | 36 | Finished | Phase 1 | [11 empty] | 0
84 | 7.4.4.1 | Accreditation assignment to accreditation set | 36 | Finished | Phase 1 | [11 empty] | 0
85 | 7.5 | Communication Management | 35 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
86 | 7.5.1 | Email configuration | 35 | Partially Done | Phase 2B | N/A | N/A | 2014-01-11 |  | 2014-01-25 |  |  | 0 | 0 | 3 | 0.6 | 3.6
87 | 7.5.2 | Notification configuration | 40 | Scheduled | Phase 2B | N/A | N/A | 2014-01-15 |  | 2014-01-25 |  |  | 0 | 0 | 2 | 0.4 | 2.4
88 | 7.6 | Activity Reports [All reports will have dashboard widget, report filters, report and role wise authorisation on report] | 41 | See below | Phase 3 | [5 empty] | These requirements are not yet defined but overall time is estimate here. | [MWP 09.01] 5 days more than we guessed in the plan? | 0 | 0 | 25 | 5 | 30
89 | 7.6.1 | Run a User report (HLS – 49) | 41 | Scheduled | Phase 3 | [5 empty] | See above for estimation. |  | N/A | N/A | N/A | N/A | 0
90 | 7.6.2 | Run an Accreditation level report (HLS – 49) | 42 | Scheduled | Phase 3 | [5 empty] | See above for estimation. |  | N/A | N/A | N/A | N/A | 0
91 | 7.6.3 | Run a Community report (HLS – 49) | 42 | Scheduled | Phase 3 | [5 empty] | See above for estimation. |  | N/A | N/A | N/A | N/A | 0
92 | 7.6.4 | Run a Activity tracking report | 42 | Scheduled | Phase 3 | [5 empty] | See above for estimation. |  | N/A | N/A | N/A | N/A | 0
93 | 7.6.5 | Run a Social Activity Report (HLS – 49) | 43 | Scheduled | Phase 3 | [5 empty] | See above for estimation. |  | N/A | N/A | N/A | N/A | 0
94 | 7.7 | Configuration Settings | 43 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
95 | 7.7.1 | Email Settings (HLS – 44) | 43 | Scheduled | Phase 2B | N/A | N/A | 2014-01-17 |  | 2014-01-25 |  |  | 0 | 0 | 2 | 0.4 | 2.4
96 | 7.7.2 | Regional Settings (HLS – 44) | 43 | Scheduled | Phase 3 | [5 empty] | Should be part of R015 theme settings |  | TBC | TBC | TBC | TBC | 0
97 | 7.7.3 | Theme Settings (HLS – 44) | 43 | Scheduled | Phase 3 | [5 empty] | Should be part of R015 theme settings |  | TBC | TBC | TBC | TBC | 0
98 | 8 | Additional Specification, Features and Functions | 43 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
99 | 8.1 | KICS API | 43 | Scoping | Phase 3 | [7 empty] | TBC | TBC | TBC | TBC | 0
100 | 8.2 | User roles | 44 | See below | Phase 2B | N/A | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | 0
101 | 8.2.1 | Administrator | 44 | Finished | Phase 1 | [11 empty] | 0
102 | 8.2.2 | Content administrator | 44 | Finished | Phase 1 | [11 empty] | 0
103 | 8.2.3 | Regional administrator | 44 | Finished | Phase 1 | [11 empty] | 0
104 | 8.2.4 | Communication administrator | 44 | Scheduled | Phase 2B | N/A | N/A | 2014-01-16 |  | 2014-01-25 |  |  | 0 | 0 | 3 | 0.6 | 3.6
105 | 8.2.5 | Report administrator | 44 | Scheduled | Phase 2B | N/A | N/A | 2014-01-20 |  | 2014-01-25 |  |  | 0 | 0 | 3 | 0.6 | 3.6
106 | 8.2.6 | Assessor | 44 | In Progress | Phase 2A | [11 empty] | 0
107 | 8.2.7 | Learner | 44 | Finished | Phase 1 | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | 0
108 | 8.3 | Security | 44 | Finished | Phase 1 | [11 empty] | 0
109 | 8.3.1 | Secure Socket Layer | 44 | Finished | Phase 1 | [11 empty] | 0
110 | 8.3.2 | Authentication | 44 | Finished | Phase 1 | [11 empty] | 0
111 | n/a | Multi-lingual System | n/a | In Progress | Phase 2A | [11 empty] | 0
112 | N/A | Multi-lingual System [English, Indonesian, Latin American Spanish, and Simplified Chinese & Portuguese] | N/A | Scheduled | Phase 2B | 2014-01-23 | 2014-01-30 | 2014-02-13 | DS/KBS | 2014-02-18 | Do we need to change images as per multi-lingual settings? | [MWP 09.01] No I don't think so. Do we have any images with text in? Are these man-days just for the Learner section? [VM 10.01] Yes, but it includes backend work to be done for resource files to be merged. UI changes time given now. | 1 | 6 | 13 | 4 | 24
113 | n/a | Analytics | n/a | Scoping | TBC | [7 empty] | TBC | TBC | TBC | TBC | 0
114 | n/a | Manual Reports | n/a | Scoping | Phase 2B | 2014-01-20 | N/A | 2014-01-29 |  | N/A | Working with Andrew |  | N/A | N/A | 5 | 0 | 5
115 | n/a | Security review | n/a | Scoping | TBC | [7 empty] | TBC | TBC | TBC | TBC | 0
116 | n/a | Adobe Connect video content linking | n/a | Scoping | TBC | [7 empty] | TBC | TBC | TBC | TBC | 0
117 | n/a | Digium surveys | n/a | Scoping | TBC | [7 empty] | TBC | TBC | TBC | TBC | 0
[13 empty] | 7.5 | 39.5 | 85 | 26.2 | 158.2
[11 empty] | Extra for TBC (Buffer) | Extra for TBC (Buffer) | 1.5 | 7.9 | 17 | 5.24 | 31.64
[13 empty] | 9 | 47.4 | 102 | 31.44 | 189.84
Note on R12: martin.pyle: Option to remove this from Phase 2B
Note on R14: martin.pyle: This could be considered for removal from Phase 2B
Note on R44: martin.pyle: Option to remove this from Phase 2B
Note on R45: martin.pyle: Option to remove this from Phase 2B
Note on R46: martin.pyle: Option to partially remove the accessibility settings aspect from Phase 2B
Note on R50: martin.pyle: This could be considered for removal from Phase 2B
Note on R54: martin.pyle: Option to remove this from Phase 2B
Note on R90: martin.pyle: Option to remove this from Phase 2B