## Sheet1
2620 - Nokia Care
Pages Status
Page | Views | Design Status | Comments
Page 1
Login | 1. Sign in | Done
| 2. Forgot password? | Done
| 3. Register | Done
Page 2
Home view | 1. Recommend a learning | Done
| 2. Form expanding | Done
| 3. Learning Activity | Done
Community view | 1. Status | Done
| 2. Nano launch | Done
| 3. Recommend a learning | Done
| 4. Form expanding | Done
| 5. Learning Activity | Done
Launch view | 1. Selected learning | Done
| 2. Recommend | Done
| 3. Rate | Done
| 4. Form expanding | Done
| 5. Learning Activity | Done
Popups
1. Welcome screen popup |  | Done
2. Nano (learning) launch panel | Video | Done
| Audio | Done
| Docs | Done
| SCO | Done
3. Personal Profile view | Learning | Done
| Accrediation | Done
| Community | Pending
4. Recent activity popup | Home/Community | Done
Known issues
Issue | Views | Status | Comments
1. The CSS3 gradiant is not working in IE9. | All | Not Started | This can be achieved by the filters. Currently it is on hold till further discussion
2. Magnet repulse effect needs to be implemented. | Home and Community | Not Started | This task requires research on it and possibly time taking.
3. Random launch of nano not functional, only sequential launching available. | Community | Not Started | This task requires research on it and possibly time taking.
Further Improvements
Improvement | Views | Status | Comments
1. Performance improvement of script | All | Not Started | List of changes for performance improvement has been created and will be applied further.
2. Minified script | All | Not Started | To be implemented after finalization
3. Abbreviated ids and classed | All | Not Started | To be implemented after finalization
4. Community discs completion status | All | Not Started | Pending